Business Analysis Mandate & Stakeholder Map

(Vertex Supply Co.)

Problem Statement
Sales growth has decelerated to 2% year-on-year, and the customer repeat purchase rate has fallen from 35% to 25% in California and Texas over the last 12 months. This dual trend is eroding revenue resilience and long-term customer value, with no clear visibility into whether the root cause lies in product, service, or market execution. The leadership team requires a structured analysis to diagnose the decline and identify targeted, data-driven interventions.

Objectives

- Improve visibility into sales performance and repeat purchase behaviour by region, channel, and customer segment.

- Identify the key drivers of the slowdown, differentiating between external market shifts and internal process/service gaps.

- Deliver a prioritized set of actionable recommendations that can be implemented within existing resources to reverse the negative trends.

Success Criteria

- A dynamic diagnostic dashboard (Power BI) accepted by the Sales Director, surfacing leading indicators of churn.

- A root-cause report quantifying the contribution of factors such as delivery delays, complaint rates, and competitive pressure.

- Three ranked intervention proposals with projected impact and implementation effort, endorsed by the regional managers and the customer service lead.

- All deliverables completed within the six-week timeline, enabling a go/no-go decision on a pilot program.

Scope

- Markets: All regions with focus on California and Texas.

- Time period: 24 months of transactional data (current and prior year) to establish trend baselines.

- Channels: Direct sales, partner resellers, and online.

- Data sources: CRM (Dynamics 365), ERP sales orders, customer service logs, and NPS survey raw data.

Constraints

- Technology stack limited to Microsoft tools (Excel, Power BI, SQL); no additional software procurement.

- Data quality issues: incomplete customer contact histories and inconsistent complaint coding must be remediated during analysis.

- Fixed six-week timeline with no budget for external research; all insights must be derived from internal data and stakeholder interviews.

Stakeholder Matrix

| Name / Role | Influence | Interest | Communication Channel |
| --- | --- | --- | --- |
| Sales Director (Sponsor) | High | High | Weekly steering updates, decision gate meetings |
| Regional Sales Managers (N/W) | Medium | High | Weekly working sessions, feedback workshops |
| Marketing Manager | Medium | Medium | Bi-weekly alignment workshops, email digests |
| IT / Data Team | Low | High | Daily stand-ups, data validation sprints |
| Customer Service Lead | Low | Medium | Ad-hoc deep-dive interviews, findings walkthrough |